Sprint 1 Plan

SlugGym — Primary MVP

# 1. Heading

| Field | Details |
| --- | --- |
| Document | Sprint 1 Plan |
| Product Name | SlugGym |
| Scrum Master | Jeongmin |
| Sprint End Date | April 22, 2026 |
| Revision | 1.0 |
| Revision Date | 2026-04-08 |

# 2. Sprint Goal

Deliver the Primary MVP of SlugGym: a working login/signup system, real-time gym headcount display via external API, and a browsable equipment catalog — establishing the core infrastructure for all future sprints.

# 3. User Stories & Tasks

## US-1.1 & US-1.2 — Account Creation & Login/Logout (5 pts)

As a gym-goer, I want to create an account and log in/out so that my data is saved and stays private.

| Task | Assignee | Est. Hours |
| --- | --- | --- |
| Define tech stack (frontend / backend / database) | Joon | 0.5h |
| Initialize project repos & set up branch strategy (main/dev/feature) | Joon | 0.5h |
| Scaffold backend project (Python + FastAPI boilerplate) | Jeongmin | 2h |
| Scaffold frontend project (React Native boilerplate) | Sangwoo | 2h |
| Design user schema (ER diagram) | Jeongmin | 2h |
| Setup authentication (JWT / session) | Jeongmin | 4h |
| Implement user signup API with input validation | Jeongmin | 4h |
| Implement user login API with error handling | Jeongmin | 4h |
| Create login / signup UI screens | Sangwoo | 4h |
| Add input validation & error messages to auth UI | Sangwoo | 2h |
| Connect frontend with auth API + handle loading states | Sangwoo | 3h |
| Write basic auth integration tests | Jeongmin | 3h |
| TOTAL |  | 34h |

## US-1.3 — Database Schema (3 pts)

As a developer, I want to set up the database schema for users, equipment, and sessions so that the app has a stable data foundation.

| Task | Assignee | Est. Hours |
| --- | --- | --- |
| Choose & provision database (PostgreSQL on cloud or local) | Joon | 2h |
| Implement DB connection & ORM setup (e.g., Prisma / Sequelize) | Joon | 3h |
| migrate user schema | Jeongmin | 2h |
| Design gym / equipment schema | Heidi | 2h |
| Design session schema (for future workout logging) | Heidi | 2h |
| Document schema decisions in GitHub Wiki | Joon | 1h |
| TOTAL |  | 12h |

## US-1.4 — Gym Headcount Display (5 pts)

As a gym-goer, I want to see the total number of people currently in the gym so that I can decide whether it is worth going.

| Task | Assignee | Est. Hours |
| --- | --- | --- |
| Research existing gym occupancy API / scraping method | Heidi | 4h |
| Implement occupancy data fetch (API or scraping) | Heidi | 6h |
| Design & implement backend endpoint for occupancy data | Heidi | 3h |
| Add fallback logic if API is unavailable (mock / manual data) | Heidi | 3h |
| Handle real-time / auto-refresh logic on frontend | Sangwoo | 4h |
| Create frontend UI to display headcount | Sangwoo | 4h |
| TOTAL |  | 24h |

## US-1.5 — Equipment Catalog (5 pts)

As a gym-goer, I want to browse a documented list of all machines available in the gym so that I can plan my workout before arriving.

| Task | Assignee | Est. Hours |
| --- | --- | --- |
| Visit gym & document all available machines (name, type, location) | Joon | 3h |
| Seed equipment data into database | Joon | 2h |
| Design & implement equipment catalog API endpoint (GET /equipment) | Joon | 4h |
| Build equipment catalog UI (list view with machine names & types) | Sangwoo | 4h |
| Add basic search / filter on equipment catalog UI | Sangwoo | 3h |
| TOTAL |  | 16h |

# 4. Team Roles & Initial Assignments

| Member | Role | First Assignment | Initial Tasks |
| --- | --- | --- | --- |
| Joon | PO / Full-stack | US-1.3 + US-1.5 | Tech stack, repo setup, DB schema, equipment catalog API |
| Sangwoo | Frontend | US-1.1 / US-1.2 | User schema design, auth API (login + signup) |
| Jeongmin | Backend + Scrum Master | US-1.1 / US-1.2 | Login/signup UI, connect frontend to auth API |
| Heidi | Backend | US-1.4 | Occupancy API research, data fetch implementation |

# 5. Scrum Meeting Schedule

| Meeting | Day | Frequency | Notes |
| --- | --- | --- | --- |
| Scrum #1 | Tuesday | Weekly (recurring) | TA visit every Tuesday |
| Scrum #2 | Thursday | Weekly (recurring) | Mid-sprint sync |
| Scrum #3 | Saturday | Weekly (recurring) | End-of-week review & blockers |

TA visits every Tuesday during the scrum meeting. All team members must be present.

# 6. Scrum Board Structure

The physical scrum board in lab and the Linear board should both follow this 4-column structure:

| User Stories | Not Started | In Progress | Completed |
| --- | --- | --- | --- |
| US-1.1, US-1.2, US-1.3, US-1.4, US-1.5 | (tasks move here) | (tasks move here) | (tasks move here) |

- Burnup chart label: 'Sprint 1 - SlugGym'

- Y-axis: story points completed (target: 18 by April 22)

- Update the board at every scrum meeting

# 7. Collaboration Tools

- GitHub: source control, pull requests, code review

- GitHub Wiki: sprint documentation, meeting notes

- Linear: task tracking, sprint board, burnup chart

- Discord: daily async communication