# Sprint 4 Plan

SlugGym — Recommendation & Polish

| Field | Details |
| --- | --- |
| Document | Sprint 4 Plan |
| Product / Team | SlugGym / Strong Slugs |
| Release | SlugGym MVP v1.0 |
| Sprint | Sprint 4 — Recommendation & Polish |
| Scrum Master | Sangwoo |
| Timeline | May 22, 2026 — June 5, 2026 |
| Revision | 1.0 · 2026-05-22 |
| Linear | Milestone: Sprint 4: Recommendation & Polish · Cycle: Sprint 4 |

## 1. Release Plan Alignment

Sprint 4 is aligned with the SlugGym MVP v1.0 Release Plan. This sprint focuses on the final recommendation and polish layer, with a planned scope of 19 story points.

- Build on authentication and user-specific data.

- Use live headcount, equipment catalog, workout logging, and realtime availability from earlier sprints.

- Connect historical congestion and routine data into a practical recommendation experience.

- Stabilize the app for final release and demo.

## 2. Sprint Goal

Deliver the final MVP recommendation layer. By the end of Sprint 4, users should be able to:

- Save and update regular workout routines.

- Receive an optimal gym visit-time recommendation based on routine and historical congestion data.

- Use an equipment-free notification MVP or a clearly documented in-app fallback.

- Run through a stable, demo-ready SlugGym MVP flow.

This sprint also finishes required Sprint 3 carryover work so recommendations rely on persisted headcount and equipment availability data instead of mock or incomplete sources.

## 3. User Stories & Tasks

US-4.1 — Routine Saving (3 pts)

Linear: SLU-157 · Priority: High

User Story: As a gym-goer, I want to save my regular workout routine so that SlugGym can use it for personalized recommendations.

#### Planned Tasks

- Define a minimal routine model: routine name, selected exercises/equipment, preferred times, and ordering.

- Build routine creation and editing from existing workout logging and equipment catalog components.

- Persist routines per authenticated user and enforce owner-only read/update access.

- Add empty, loading, error, and saved-state UI.

- Add deterministic tests for create, edit, delete, empty, and error states.

#### Acceptance Criteria

- Users can create, update, and delete routines.

- Routines are tied to the authenticated user.

- Routine UI handles loading, empty, and error states safely.

- Tests cover the core routine-saving flow.

US-4.2 — Optimal Time Recommendation (8 pts)

Linear: SLU-158 · Priority: High

User Story: As a gym-goer, I want a recommended time to visit the gym based on my routine and historical congestion data so that I can avoid waiting for equipment.

#### Planned Tasks

- Use saved routine data to identify the equipment types a user is likely to need.

- Use persisted historical headcount and congestion data to compute quieter time windows.

- Combine user routine preferences with weekly congestion buckets to recommend a practical visit time.

- Show a recommendation card with clear confidence and fallback copy when data is sparse.

- Document the recommendation logic for the final demo.

- Add tests for recommendation ranking, sparse-data fallback, and UI rendering.

#### Acceptance Criteria

- Recommendation uses routine inputs and historical congestion/headcount data when available.

- Sparse or unavailable data produces conservative fallback messaging.

- Recommendation logic is explainable during the final demo.

- Tests cover ranking and fallback behavior.

US-4.3 — Equipment-Free Notification (5 pts)

Linear: SLU-159 · Priority: High

User Story: As a gym-goer, I want to be notified when busy equipment becomes free so that I can act in real time.

#### Planned Tasks

- Confirm whether native push notifications are feasible within the remaining Expo/Supabase timeline.

- If feasible, let users opt into notifications for busy equipment or routine-related equipment.

- Trigger notifications when realtime availability changes from occupied/busy to available.

- If native push is too risky, ship an in-app notification fallback and document native push as deferred.

- Add tests for opt-in state and trigger logic without relying on live external services.

#### Acceptance Criteria

- Notification behavior is implemented or explicitly deferred with an in-app fallback.

- Users have a clear opt-in or watchlist interaction.

- Trigger logic is testable without live external services.

- Linear comments document the chosen implementation path.

US-4.4 — Bug Fixes & Polish (3 pts)

Linear: SLU-160 · Priority: High

User Story: As a team preparing for final release, we want the app to be stable, polished, and demo-ready.

#### Planned Tasks

- Fix existing typecheck failures in the workout/exercise history data path.

- Resolve the existing lint warning in EquipmentAvailabilityMap.tsx.

- Review navigation labels, empty-state copy, error messages, and loading states across core screens.

- Run final verification on the release branch: tests, lint, typecheck, and manual smoke test.

- Prepare the final demo flow across login, headcount, equipment catalog, workout logging, realtime availability, map/history, routine saving, and recommendation.

#### Acceptance Criteria

- Final verification gates pass.

- Main user flows are stable enough for demo.

- Final copy and fallback states are clear.

- Release/demo blockers are fixed or explicitly documented.

## 4. Team Roles & Initial Assignments

| Member | Role / Sprint Focus | Initial Focus Areas |
| --- | --- | --- |
| Sangwoo | Frontend integration, recommendation UI, fallback states, testing | Routine UI, recommendation card, equipment/history data wiring, final polish |
| Dareum / DA | Supabase/backend support, RLS, scheduled data persistence | Routine persistence, headcount persistence, notification feasibility support |
| Jeongmin / JL | Recommendation algorithm and historical aggregation logic | Recommendation scoring, congestion bucket validation, demo explanation support |
| Heidi / HE | Review and QA support | Workout/exercise data path review, notification fallback review, final polish |

## 5. Scrum Meeting Schedule

- Tuesday: TA visit / sprint checkpoint.

- Thursday: Mid-sprint implementation sync.

- Saturday: End-of-week review, blockers, and PR status.

TA visits happen every Tuesday during the scrum meeting. All team members should be present.

## 6. Scrum Board Structure

The physical scrum board and Linear board should follow the same flow:

- User Stories → Not Started → In Progress → In Review → Completed.

- Burnup chart label: Sprint 4 - SlugGym.

- Y-axis: story points completed.

- Target: 19 story points by June 5.

- Update Linear at every scrum meeting.

## 7. Carryover Dependencies from Sprint 3

- Historical headcount pipeline: complete schema, polling, aggregation, and Popular Times integration so recommendations can use persisted data.

- Equipment availability map: merge final review/test work while preserving loading, empty, error, free, occupied, and unknown status behavior.

- Realtime resilience: keep reconnect/backoff behavior and stale-data tests for reliable live equipment availability.

- Workout history: ensure past workout logs continue to render correctly after routine and recommendation changes.

## 8. Collaboration Tools

- GitHub: source control, pull requests, and code review.

- GitHub Wiki: sprint documentation and release plan.

- Linear: task tracking, sprint board, milestone, and burnup chart.

- Discord: async communication and blocker updates.

- Obsidian: personal meeting notes and planning drafts.

## 9. Risks & Scope Control

- Sparse historical data: use confidence/fallback messaging and keep recommendations conservative until enough samples exist.

- Push notification scope: prioritize opt-in + trigger logic first; use in-app alerts as fallback if native push setup is unstable.

- Routine schema expansion: keep the MVP routine model minimal and avoid v2 fields such as class schedule integration or social sharing.

- Type/lint regressions: prioritize typecheck and lint cleanup before final demo preparation.

- Final sprint capacity: prioritize routine saving, recommendation, and release stability over lower-value polish.

## 10. Definition of Done

A Sprint 4 task is done when:

- Code is merged into the target branch or documentation is published.

- Tests pass locally for affected areas.

- Relevant UI states include loading, empty, error, and sparse-data fallbacks.

- Linear issue has a concise implementation/update comment.

- Related parent issue progress is updated.

- Final release gates pass: tests, lint, typecheck, and manual smoke test.

## 11. Proposed Timeline

- Day 1–2: Merge Sprint 3 visualization/headcount carryover and finalize routine-saving data contract.

- Day 3–4: Implement routine saving UI, persistence, and tests.

- Day 5–7: Implement recommendation ranking and recommendation UI using routine + historical congestion data.

- Day 8: Evaluate and implement equipment-free notification MVP or documented fallback.

- Day 9: Run bug fixes, typecheck/lint cleanup, and full regression testing.

- Day 10: Prepare final demo, release notes, and merge decision.

## 12. Expected Deliverables

- Routine saving flow and persistence.

- Optimal time recommendation card backed by saved routine and historical congestion data.

- Equipment-free notification MVP or documented fallback.

- Completed historical headcount / Popular Times carryover integration.

- Final bug-fix and polish pass for SlugGym MVP v1.0.

- Passing final verification and demo-ready release branch.