# Sprint 3 Plan

SlugGym — Visualization

| Field | Details |
| --- | --- |
| Document | Sprint 3 Plan |
| Product / Team | SlugGym / Strong Slugs |
| Sprint | Sprint 3 — Visualization |
| Scrum Master | Sangwoo |
| Timeline | May 8, 2026 — May 20, 2026 |
| Revision | 1.0 · 2026-05-08 |
| Linear | Milestone: Sprint 3: Visualization · Cycle: Sprint 3 |

# 1. Sprint Goal

Deliver the visualization layer of SlugGym. By the end of Sprint 3, users should be able to understand current gym congestion, review past workout history, and—if capacity allows—view weekly congestion patterns to identify quieter time slots.

- Current-state visibility: show a visual equipment availability map with clear status colors.

- Workout review: let users inspect past workout history and detail views safely.

- Historical insight: provide a weekly congestion heatmap when the data source is reliable enough.

- Foundation: build on Sprint 2's workout logging and realtime equipment availability infrastructure.

# 2. Planned User Stories

### US-3.1 — Equipment Availability Map (8 pts)

Linear: SLU-128 · Priority: High

User Story

As a gym-goer, I want to see a visual map of equipment availability, color-coded by status, so that I can understand gym congestion at a glance.

Planned Tasks

- SLU-131 — Define equipment map layout data contract · Owner: Joon / DA · 2h

- SLU-141 — Wire availability map data to occupancy/equipment state · Owner: Jeongmin / JL · 4h

- SLU-132 — Build equipment availability map UI · Owner: Sangwoo · 6h

- SLU-133 — Add map loading, empty, and error states · Owner: Sangwoo · 2h

- SLU-142 — Test equipment map status rendering · Owner: Jeongmin / JL · 3h

- Estimated total: 17h

Acceptance Criteria

- Equipment is grouped visually by zone/layout.

- Free, occupied, and unknown states are represented clearly with a legend.

- UI handles loading, empty, and error states.

- Tests cover core status rendering and fallback states.

### US-3.2 — Past Workout History (3 pts)

Linear: SLU-129 · Priority: High

User Story

As a gym-goer, I want to view my past workout logs so that I can track my consistency over time.

Planned Tasks

- SLU-134 — Audit existing session history against US-3.2 · Owner: Sangwoo · 1h

- SLU-135 — Add workout history detail view · Owner: Sangwoo · 4h

- SLU-136 — Verify history detail data contract · Owner: Heidi / HE · 2h

- SLU-137 — Add tests for history and detail states · Owner: Sangwoo · 2h

- Estimated total: 9h

Acceptance Criteria

- Existing SLU-89 history work is reviewed and not duplicated.

- Users can open completed workouts and see detail data when available.

- Missing detail data has a safe fallback.

- Tests cover loading, empty, error, and normal rendering states.

### US-3.3 — Weekly Congestion Heatmap (5 pts)

Linear: SLU-130 · Priority: Medium

User Story

As a gym-goer, I want to see a weekly congestion heatmap for each equipment type so that I can identify historically quieter time slots.

Planned Tasks

- SLU-138 — Define weekly congestion heatmap data source · Owner: Heidi / HE · 2h

- SLU-143 — Implement weekly congestion aggregation helper · Owner: Jeongmin / JL · 4h

- SLU-139 — Build weekly congestion heatmap UI · Owner: Sangwoo · 5h

- SLU-140 — Add no-data fallback for heatmap · Owner: Sangwoo · 1.5h

- SLU-144 — Test heatmap aggregation and rendering · Owner: Jeongmin / JL · 2.5h

- Estimated total: 15h

Acceptance Criteria

- Team agrees on data source before implementation.

- Congestion data is grouped into day/hour buckets.

- Heatmap has a clear legend and no-data fallback.

- Feature avoids misleading recommendations if data is sparse.

- If capacity is limited, this story can be reduced or moved to backlog.

# 3. Team Focus

| Member | Sprint 3 Focus | Initial Tasks |
| --- | --- | --- |
| Joon / DA | PO / full-stack; map data contract and parent issue tracking | SLU-131, parent US tracking |
| Sangwoo | Frontend; map UI, history detail UI, heatmap UI, FE tests | SLU-132, SLU-133, SLU-134, SLU-135, SLU-137, SLU-139, SLU-140 |
| Jeongmin / JL | Backend + scrum support; data wiring, aggregation helpers, visualization tests | SLU-141, SLU-142, SLU-143, SLU-144 |
| Heidi / HE | Backend / Supabase; history data contract and heatmap data source | SLU-136, SLU-138 |

# 4. Scrum Cadence

- Tuesday — Scrum #1: TA visit / sprint checkpoint.

- Thursday — Scrum #2: mid-sprint implementation sync.

- Saturday — Scrum #3: end-of-week review, blockers, and PR status.

- TA visits happen every Tuesday during scrum; all team members should attend.

# 5. Board & Tracking

Linear and the physical scrum board should use the same flow: User Stories → Not Started → In Progress → In Review → Completed.

- Burnup chart label: Sprint 3 - SlugGym.

- Y-axis: story points completed.

- Target: 16 story points by May 20.

- Update Linear at every scrum meeting.

# 6. Collaboration Tools

- GitHub — source control, pull requests, and code review.

- GitHub Wiki — sprint documentation and release plan.

- Linear — task tracking, sprint board, and burnup chart.

- Discord — daily async communication and blocker updates.

- Obsidian — personal meeting notes and planning drafts.

# 7. Risks & Scope Control

- Sprint 2 carry-over PRs may delay Sprint 3 start → review and merge carry-over PRs early.

- Map layout metadata may be undefined → DA defines the data contract before UI implementation.

- Heatmap data may be sparse → add no-data fallback and demote US-3.3 if needed.

- Realtime data contracts may change → reuse existing hooks and avoid duplicate subscriptions.

- Midterm period may reduce capacity → prioritize US-3.1 and US-3.2; treat US-3.3 as stretch if needed.

# 8. Definition of Done

A Sprint 3 task is considered done when:

- Code is merged into the target branch or documentation is published.

- Tests pass locally for the affected areas.

- Relevant UI states include loading, empty, and error handling.

- The Linear issue has a concise implementation/update comment.

- Related parent issue progress is updated.